# CallE — Intelligent Model Router

Reducing enterprise GenAI operating cost without sacrificing support quality or safety

Role: Hybrid AI Product Manager + AI Project Manager

Company: CallE

Industry: B2B customer-support SaaS

Delivery horizon: 12–16 weeks for MVP / pilot

Primary KPI: AI Cost per Resolved Interaction

____________________________________________________________

## Evidence & Disclosure

This is a simulated case study. It is designed to demonstrate product judgment, AI decision-making, technical understanding, and project delivery not to claim real CallE production outcomes.

| Label | Meaning |
| --- | --- |
| FACT | Information established in the case-study brief |
| ASSUMPTION | A reasonable value used because real information is unavailable |
| HYPOTHESIS | A proposition the MVP is designed to test |
| TARGET | A desired future outcome |
| SIMULATED / ILLUSTRATIVE | Example analysis used to demonstrate decision-making |

No simulated customers, research, benchmarks, financial results, production deployments, or AI performance are presented as real evidence.

____________________________________________________________

# 1. The Hook

CallE processes approximately 100,000 AI support interactions per month, with every request currently routed to the highest-capability model selected as its baseline.

The product question is not:

“Which LLM is best?”

It is:

Can CallE reduce the cost of resolving customer issues while maintaining an agreed quality threshold and keeping risky decisions under human control?

That reframes the problem from model selection into business-value optimisation under quality, cost, latency, reliability, privacy, and safety constraints.

# 2. Executive Summary

CallE is a B2B customer-support SaaS platform whose AI capability helps customers resolve support issues and helps human support agents handle escalated cases.

The current workflow uses a premium LLM for every interaction.

This creates a potential economic inefficiency because support requests vary substantially in:

- Complexity

- Token volume

- Risk

- Context requirements

- Need for reasoning

- Need for human intervention

A simple FAQ should not automatically consume the same model capability as a complex troubleshooting request. Conversely, a high-risk security or payment issue should not be routed to a cheaper model merely because it is cheaper.

### Proposed solution

Build a hybrid intelligent model router that combines:

- Deterministic safety and business rules

- AI-assisted intent and complexity classification

- A model-selection policy

- Response validation

- Premium-model fallback

- Human escalation

### Primary objective

Reduce AI Cost per Resolved Interaction while maintaining quality at or above the premium-model baseline.

### Secondary objectives

- Increase automated resolution

- Reduce unnecessary premium-model usage

- Reduce human support workload

- Improve escalation quality

- Establish repeatable model governance

The project is intentionally structured as a controlled hypothesis-validation exercise.

# 3. Business Context

## 3.1 Company

CallE is a B2B customer-support SaaS company.

Its product provides AI-assisted customer support across business-specific support workflows.

## 3.2 Primary users

### Customers

Customers interact with CallE to:

- Ask support questions

- Troubleshoot problems

- Obtain product information

- Resolve routine issues

- Escalate unresolved issues

### Support agents

Agents handle cases that AI cannot safely or reliably resolve.

They need:

- A concise issue summary

- Customer intent

- Relevant context

- Suggested category

- Suggested response

- Reason for escalation

- Confidence / risk signal

## 3.3 Business problem

FACT: The scenario assumes 100,000 AI interactions per month and a premium-model workflow for every request.

PRODUCT PROBLEM: CallE may be paying premium-model economics for requests that do not require premium-model capability.

But simply moving requests to cheaper models could reduce quality or increase human workload.

Therefore the actual problem is:

How can CallE optimise model economics while protecting customer experience, support operations, and safety?

# 4. Why the Problem Matters

If CallE does nothing:

- AI infrastructure/API spend may grow with usage.

- Premium-model usage remains high.

- Simple requests may consume unnecessary capability.

- The company has limited ability to optimise model economics by request type.

- Human workload may remain unnecessarily high when AI fails without useful escalation context.

If CallE over-optimises:

- Quality may fall.

- More requests may require human intervention.

- High-risk cases could be mishandled.

- Customer trust could decline.

- Apparent AI savings could become operational costs.

The strategic objective is therefore:

Optimise the economics of successful, safe resolution,not merely the price of an LLM call.

# 5. Root Cause

The visible problem is:

AI costs are high.

The deeper product problem is:

The current workflow does not differentiate model capability requirements across heterogeneous support requests.

A support platform receives:

- Simple FAQs

- Summaries

- Classification

- Standard troubleshooting

- Complex reasoning

- Long-context questions

- Ambiguous requests

- High-risk requests

These have different capability and risk profiles.

# 6. AI Opportunity Map

| Problem | Traditional solution | AI opportunity | Human role | Recommendation |
| --- | --- | --- | --- | --- |
| Simple FAQ | Static rules/search | Lightweight model where appropriate | Exception handling | Automate |
| Classification | Rules / ML classifier | AI-assisted classification | Review edge cases | Hybrid |
| Summarisation | Template/rules | LLM summarisation | Validate escalation context | Automate with controls |
| Troubleshooting | Decision trees | Model + authorised context | Escalate failures | Hybrid |
| Complex reasoning | Rules become difficult | Higher-capability model | Review when uncertain | Premium + controls |
| High-risk request | Deterministic policy | AI assists interpretation | Human decision | Human-controlled |
| Account-specific action | Workflow automation | AI can interpret intent | Authorised agent performs action | Human-controlled |
| Uncertain response | Retry/rules | Confidence + validation | Human review | Escalate |

### Product conclusion

AI is useful for interpreting variable natural-language requests, but deterministic rules and humans remain essential for safety-critical decisions.

# 7. Product Vision

Make every CallE AI interaction economically efficient without compromising the quality or safety of customer support.

## Mission

Route each support request to the least expensive eligible model capable of safely resolving that request, with validation, fallback, and human escalation when necessary.

## Product goal

Validate whether intelligent routing can improve unit economics while preserving the quality of the existing premium-model workflow.

## Value proposition

For CallE:

Use premium AI capability where it creates value, not by default.

For customers:

Receive fast, reliable support with human intervention when automation is inappropriate.

For support agents:

Receive better-prepared escalations instead of starting each case from scratch.

# 8. Product Strategy

## Principle 1 — Quality before optimisation

Cost reduction is only valuable if support quality remains acceptable.

## Principle 2 — Risk overrides cost

A high-risk request should never be routed to a cheaper model simply because it is cheaper.

## Principle 3 — Capability-based routing

The decision should be:

“What is the least expensive eligible capability for this request?”

not:

“What is the cheapest model?”

## Principle 4 — Human escalation is a product outcome

Some requests should deliberately leave the automated path.

## Principle 5 — Evidence before scale

The routing strategy must be validated experimentally before broad rollout.

# 9. Current-State Journey

### Current pain points

- Every request receives premium-model capability.

- Model cost is not differentiated by request requirements.

- Failed AI interactions create human workload.

- Agents may need to reconstruct the conversation.

- There is limited routing intelligence between request characteristics and model selection.

# 10. Future-State Journey

# 11. Routing Logic

The router evaluates four major dimensions:

### 1. Risk

Is automation permitted?

### 2. Complexity

What level of reasoning is required?

### 3. Context requirement

Does the request require authorised support context?

### 4. Confidence

Is the system sufficiently confident to proceed?

Then the policy engine considers:

- Quality eligibility

- Cost

- Latency

- Reliability

- Privacy/security

- Model availability

# 12. Routing Policy

Incoming request
       |
       v
Risk assessment
       |
       +---- High risk ------------------> Human escalation
       |
       v
Intent / complexity / context
       |
       v
Eligible-model policy
       |
       +---- Simple / low risk ----------> Lower-cost eligible model
       |
       +---- Moderate -------------------> Mid-tier eligible model
       |
       +---- Complex --------------------> Premium model
       |
       v
Response validation
       |
       +---- Pass -----------------------> Customer
       |
       +---- Fail -----------------------> Premium fallback
                                             |
                                             +-- Safe resolution --> Customer
                                             |
                                             +-- Still unresolved --> Human

# 13. High-Risk Guardrails

The following cases should bypass normal cost optimisation or require human review:

- Refund/payment disputes

- Account/security issues

- Highly frustrated customers

- Sensitive personal information

- Requests requiring account-specific actions

- Medical/safety-related queries

- AI uncertainty / low confidence

- Other business-specific risks

### Guardrail principle

A request can be cheap to process but expensive to get wrong.

Therefore risk is a hard eligibility constraint, not simply another weighted score.

# 14. Human-in-the-Loop Design

## AI completely resolves the issue

Customer → AI → validated answer → resolved

## AI cannot safely resolve

Customer
   ↓
AI attempt
   ↓
Validation failure / uncertainty / risk
   ↓
Ticket creation
   ↓
Human agent
   ↓
Investigation
   ↓
Agent response
   ↓
Resolution

The human path is not treated as an AI failure alone.

The product should optimise the handoff quality.

# 15. Agent Context Pack

When AI escalates a case, the agent should receive:

| Field | Purpose |
| --- | --- |
| Issue summary | Understand the case quickly |
| Customer intent | Understand what the customer wants |
| Suggested category | Speed up triage |
| Relevant knowledge/context | Reduce investigation effort |
| Suggested response | Accelerate drafting |
| Actions attempted | Avoid duplicate work |
| Reason for escalation | Explain why automation stopped |
| Confidence/risk signal | Support agent judgment |

### Product principle

When AI cannot resolve the issue, it should still reduce the human's work.

# 16. RAG Decision

RAG is deliberately not a new MVP build.

CallE can use existing authorised support-context capabilities where available.

Potential knowledge sources include:

- FAQs

- Product documentation

- Previous support tickets

- Internal policies

- Troubleshooting guides

### MVP boundary

Use existing authorised retrieval/context capabilities; do not build a new RAG/vector infrastructure layer during MVP.

### Phase 2

Evaluate a dedicated retrieval architecture if pilot evidence shows it is necessary.

This protects the MVP from unnecessary technical scope.

# 17. Product Requirements

## Functional Requirements

### FR-001 — Risk Classification

The system shall identify requests that require mandatory human review.

Acceptance criteria

- Given a request matching a mandatory high-risk condition

- When the routing process begins

- Then the request is prevented from entering the normal low-cost automated path.

### FR-002 — Complexity Classification

The system shall classify the approximate complexity/capability requirement of an interaction.

### FR-003 — Context Assessment

The system shall determine whether authorised support context is required for reliable resolution.

### FR-004 — Model Selection

The system shall select an eligible model according to the routing policy.

### FR-005 — Response Validation

The system shall validate generated responses before automated delivery.

Validation should consider:

- Correctness

- Relevance

- Completeness

- Safety

- Groundedness where applicable

- Confidence

- Resolution suitability

### FR-006 — Premium Fallback

If a lower-cost model fails validation but the request remains safe for automation, the system shall retry using the premium baseline.

### FR-007 — Human Escalation

The system shall create/escalate a support case when:

- The request is high risk.

- Confidence is insufficient.

- Validation fails critically.

- Premium fallback cannot safely resolve the issue.

### FR-008 — Agent Context Pack

Escalated cases shall contain structured AI-generated context.

### FR-009 — Automated Resolution

An interaction shall be counted as AI-resolved only when the issue is completely resolved without human involvement.

### FR-010 — Audit Trail

The system shall retain the routing and outcome path for evaluation and governance.

# 18. Non-Functional Requirements

### NFR-001 — Security

- Authentication

- Authorisation

- PII controls

- Secure API communication

- Vendor data-use review

- Access logging

### NFR-002 — Performance

Routing and validation must stay within an acceptable support latency budget.

### NFR-003 — Availability

A model/API failure must not become a single point of failure for support.

### NFR-004 — Scalability

The architecture must support increasing interaction volume without requiring a proportional increase in premium-model usage.

### NFR-005 — Auditability

Routing decisions and escalation reasons should be traceable.

# 19. AI Requirements

### AIR-001

Model routing must respect mandatory safety constraints.

### AIR-002

Model eligibility must be evaluated by support-task category, not only overall average performance.

### AIR-003

Lower-cost models must have a safe fallback path.

### AIR-004

AI-generated customer responses must be validated before automated delivery.

### AIR-005

Model/policy changes must be evaluated against the established benchmark before controlled deployment.

# 20. User Stories

As a customer, I want CallE to resolve routine support issues quickly so that I don't need to wait for a human agent.

As a support agent, I want escalated cases to contain a clear issue summary and context so that I can investigate faster.

As a product manager, I want to measure cost per resolved interaction so that I can determine whether routing creates real economic value.

As a support leader, I want risky requests escalated to humans so that automation does not compromise customer safety or trust.

# 21. Prioritisation

For this MVP, MoSCoW is appropriate because the immediate delivery problem is scope control within a 12–16 week window.

| Capability | Priority | Rationale |
| --- | --- | --- |
| Risk classification | Must | Safety gate |
| Complexity classification | Must | Core routing input |
| Model routing | Must | Core hypothesis |
| Response validation | Must | Quality gate |
| Premium fallback | Must | Recovery path |
| Human escalation | Must | Safety/resolution |
| Agent context pack | Must | Reduce handoff cost |
| Automated resolution | Must | Primary outcome |
| Historical-ticket context | Must | Support workflow |
| Customer-facing AI | Must | Core user experience |
| Agent assist | Must | Handoff efficiency |
| New RAG infrastructure | Won't — MVP | Scope control |
| Executive dashboard | Won't — MVP | Measurement can exist without UI |
| Fine-tuning | Won't — MVP | Not required to test hypothesis |
| Voice support | Won't — MVP | Unrelated to core hypothesis |
| Autonomous financial actions | Won't — MVP | High risk |

# 22. Roadmap

## Discovery

Define the business problem, baseline, benchmark and guardrails.

## Prototype

Prove routing and fallback mechanics.

## MVP

Build the end-to-end controlled workflow.

## Pilot

Compare dynamic routing against the premium baseline.

## Production

Deploy only after pilot gates pass.

## Scale

Expand model coverage, categories, retrieval and channels based on evidence.

# 23. Technology Decision

## Options considered

| Option | Strength | Weakness | Decision |
| --- | --- | --- | --- |
| Premium model for all requests | Strong quality baseline | High cost | Baseline |
| Cheapest model for all | Low model cost | Quality/safety risk | Reject |
| Rules only | Explainable | Limited language flexibility | Insufficient |
| LLM chooses everything | Flexible | Governance/opacity risk | Reject |
| Single-model optimisation | Simple | Provider dependency | Limited |
| Hybrid routing | Flexible + controllable | More orchestration | Recommend |

### Recommended architecture

Hybrid routing with deterministic safety controls, AI-assisted classification, policy-based model selection, validation, premium fallback and human escalation.

# 24. Architecture

## Component responsibilities

### Risk engine

Determines whether automated handling is permitted.

### Complexity / intent analysis

Interprets the natural-language request.

### Context assessment

Determines whether authorised support information is required.

### Routing policy engine

Applies model eligibility rules and optimisation criteria.

### Model layer

Generates the response.

### Validator

Checks output quality and safety.

### Fallback

Provides a recovery path.

### Human escalation

Provides safe resolution when automation is inappropriate.

### Audit/evaluation data

Supports measurement, troubleshooting and governance.

# 25. Product Manager vs Technical Ownership

A critical boundary in this project:

| Area | Product Manager | Engineering | ML/AI | Project Manager |
| --- | --- | --- | --- | --- |
| Business problem | Own | Consult | Consult | Consult |
| PRD | Own | Input | Input | Input |
| Routing policy | Define | Implement | Advise | Track delivery |
| Quality threshold | Define | Support | Measure/evaluate | Track |
| Model implementation | Decide requirements | Build | Optimise/evaluate | Coordinate |
| Architecture | Contribute | Own technical design | Contribute | Coordinate |
| AI benchmark | Define decision need | Support | Execute | Track |
| Security controls | Define requirements | Implement | Support | Coordinate |
| Delivery plan | Define priorities | Estimate | Estimate | Own |
| Risks | Product risks | Technical risks | AI risks | Own project RAID |
| Pilot decision | Recommend | Provide evidence | Provide evidence | Coordinate |

The PM is not claiming to have personally built every technical component.

The role is to:

Identify the problem → define the product → translate requirements → work with technical teams → make informed AI decisions → manage delivery → manage risks → measure outcomes.

# 26. Model Evaluation Framework

## Evaluation dimensions

| Dimension | Weight |
| --- | --- |
| Answer quality | 30% |
| Cost | 25% |
| Latency | 15% |
| Reliability | 10% |
| Context capability | 10% |
| Privacy/security | 10% |
| Total | 100% |

### Important decision rule

The weights are CallE product decisions for this hypothetical case, not universal industry standards.

A model that fails a mandatory safety/security requirement cannot compensate through a higher weighted score.

# 27. Benchmark Design

### Benchmark size

ASSUMPTION: 180 curated support scenarios.

| Category | Cases |
| --- | --- |
| Simple FAQ | 20 |
| Standard support | 20 |
| Summarisation / classification | 20 |
| Troubleshooting | 20 |
| Complex reasoning | 20 |
| Long-context | 20 |
| Ambiguous requests | 20 |
| High-risk | 20 |
| Adversarial / prompt injection | 20 |
| Total | 180 |

### Benchmark disclosure

SIMULATED / CURATED BENCHMARK DESIGN

The benchmark is not claimed to represent CallE's actual customer population.

# 28. AI Evaluation

## Model quality

Evaluate:

- Correctness

- Precision/recall where applicable

- Groundedness

- Relevance

- Completeness

## AI safety

Evaluate:

- Hallucination

- PII leakage

- Prompt injection

- Unsafe outputs

- Bias where relevant

## Product performance

Evaluate:

- Task completion

- Automated resolution

- Human escalation

- Agent time saved

- Latency

## Business performance

Evaluate:

- AI cost

- AI Cost per Resolved Interaction

- Productivity

- ROI

# 29. Experiment Design

## Hypothesis

If CallE routes lower-risk and lower-complexity interactions to appropriately capable lower-cost models while reserving premium capability for requests that genuinely require it, then AI Cost per Resolved Interaction can decrease without reducing quality below the premium baseline.

## Control

100% of eligible requests
        ↓
Premium baseline

## Treatment

Risk-aware dynamic routing
        ↓
Eligible model
        ↓
Validation
        ↓
Fallback / escalation where required

## Primary success metric

AI Cost per Resolved Interaction

## Quality threshold

Treatment quality ≥ premium baseline

## Safety threshold

No critical safety threshold breach

## Decision rule

Proceed only if:

- Economic improvement is meaningful.

- Quality remains at or above the agreed baseline.

- Mandatory safety controls pass.

- Operational impact is acceptable.

# 30. Economics

## Baseline

The baseline cost model begins with:

100,000 monthly interactions × premium-model cost per interaction

But request sizes vary, so a more realistic model needs token-volume assumptions.

### Illustrative request profiles

| Profile | Input tokens | Output tokens |
| --- | --- | --- |
| Short | 500 | 150 |
| Medium | 1,500 | 400 |
| Long | 4,000 | 1,000 |

These values are ASSUMPTIONS, not CallE measurements.

## Cost model

For each interaction:
Model cost = input tokens × input price + output tokens × output price

At product level:
AI Cost per Resolved Interaction = Total variable AI cost ÷ AI-resolved interactions

A complete economic model should also include:

- Routing/classification cost

- Validation cost

- Fallback calls

- Retrieval/context costs where applicable

- Human operational impact

# 31. Why Cost per Request Is Not Enough

Consider two hypothetical strategies:

### Strategy A

Very cheap model.

- Low AI cost

- Poor resolution

- High escalation

### Strategy B

Moderately higher AI cost.

- Higher resolution

- Lower escalation

- Better customer outcomes

Strategy A may look better if we only measure:

Cost per interaction

But Strategy B may create more business value.

Therefore the primary economic KPI is:

AI Cost per Resolved Interaction

# 32. Illustrative Scenario — Not a Result

The following is deliberately SIMULATED / ILLUSTRATIVE.

| Strategy | Cost | Quality | Interpretation |
| --- | --- | --- | --- |
| All premium | High | Strong | Safe baseline; weak optimisation |
| Aggressive low-cost routing | Low | Below threshold | Reject |
| Balanced routing | Lower | At/above threshold | Potential candidate |

The product decision is not:

“Choose the strategy with the lowest cost.”

It is:

Choose the strategy that creates acceptable economic improvement while preserving quality and safety.

# 33. KPI Framework

## North-star economic KPI

### AI Cost per Resolved Interaction

Measures economic efficiency of actual AI resolution.

## Quality guardrail

### Quality score

Treatment must remain at or above the premium baseline.

## Safety guardrails

- Critical safety failure rate

- PII leakage

- Unsafe automation

- Incorrect high-risk routing

## Supporting metrics

| Metric | Purpose |
| --- | --- |
| Automated resolution rate | AI effectiveness |
| Premium-model usage % | Routing efficiency |
| Fallback rate | Routing quality |
| Human escalation rate | Workload transfer |
| Cost / interaction | Raw economics |
| Cost / resolved interaction | Primary economic KPI |
| Latency | Customer experience |
| Quality score | Primary guardrail |
| Safety failure rate | Critical guardrail |

# 34. Project Charter

## Objective

Validate whether intelligent model routing can reduce CallE's AI Cost per Resolved Interaction without reducing quality below the premium baseline.

## Scope

Design, build and pilot:

- Risk classification

- Complexity classification

- Model routing

- Response validation

- Premium fallback

- Human escalation

- Agent context

- Automated resolution

## Out of scope

- New RAG infrastructure

- Autonomous refunds

- Autonomous payment decisions

- Autonomous account changes

- Fine-tuning

- Custom foundation model

- Voice

- Global expansion

- Executive dashboard

## Deliverables

- PRD

- Evaluation benchmark

- Routing policy

- Prototype

- MVP

- Security assessment

- UAT

- Pilot

- Executive recommendation

## Timeline

12–16 weeks

## Constraints

- Quality cannot fall below the agreed baseline.

- High-risk automation must remain controlled.

- Model/API providers create external dependencies.

- MVP scope must remain limited.

# 35. Work Breakdown Structure

## 1. Discovery

- Stakeholder alignment

- Current-state mapping

- Business objectives

- Baseline definition

- Risk taxonomy

## 2. Requirements

- PRD

- User stories

- Acceptance criteria

- AI requirements

- Safety requirements

## 3. UX / Workflow

- Customer journey

- Escalation journey

- Agent context design

- Failure states

## 4. Architecture

- Routing architecture

- Policy engine

- Model integrations

- Fallback architecture

- Audit design

## 5. AI Development

- Benchmark

- Risk classification

- Complexity classification

- Evaluation

- Validation

## 6. Engineering

- Orchestration

- APIs

- Ticket integration

- Agent workflow

- Logging

## 7. Testing

- Functional QA

- AI evaluation

- Safety testing

- Adversarial testing

- Integration testing

## 8. Security

- PII

- Vendor review

- Prompt injection

- Access control

- Data retention

## 9. UAT

- Support SME testing

- Acceptance criteria

- Defect resolution

## 10. Pilot

- Control

- Treatment

- KPI measurement

- Failure analysis

## 11. Launch

- Readiness review

- Controlled release

- Rollback plan

## 12. Monitoring

- Quality

- Cost

- Resolution

- Escalation

- Model review

# 36. 14-Week Delivery Plan

| Phase | Weeks | Key deliverable |
| --- | --- | --- |
| Discovery & baseline | 1–2 | Product requirements + evaluation framework |
| Model evaluation | 3–4 | Model evaluation report |
| Routing prototype | 5–7 | Working routing prototype |
| Support workflow | 8–9 | End-to-end escalation workflow |
| Testing & UAT | 10–11 | MVP readiness assessment |
| Controlled pilot | 12–14 | Pilot evidence + recommendation |
| Contingency | 15–16 | Calibration / remediation if required |

The 14-week plan is the baseline; weeks 15–16 provide contingency for remediation or optimisation.

# 37. Sprint Plan

## Sprint 1 — Baseline

Objective: Establish current state.

Tasks

- Current-state mapping

- KPI definitions

- Risk taxonomy

- Benchmark specification

Definition of Done

- Baseline workflow documented

- KPI definitions approved

- Evaluation scope agreed

## Sprint 2 — Model Evaluation

Objective: Establish model eligibility.

Tasks

- Candidate model selection

- Benchmark dataset

- Evaluation rubric

- Cost model

- Initial testing

Definition of Done

- Benchmark executable

- Evaluation criteria approved

- Initial eligibility matrix available

## Sprint 3 — Routing Prototype

Objective: Prove the core routing mechanism.

Tasks

- Risk classification

- Complexity classification

- Policy engine

- Model integration

Definition of Done

- Requests can be routed

- Routing decisions are logged

- Basic fallback path exists

## Sprint 4 — Validation & Fallback

Objective: Make routing safe and recoverable.

Tasks

- Response validation

- Quality gates

- Premium fallback

- Failure handling

Definition of Done

- Invalid responses are blocked

- Safe failures reach premium fallback

- Critical failures escalate

## Sprint 5 — Agent Workflow

Objective: Improve human handoff.

Tasks

- Ticket creation

- Issue summary

- Intent

- Suggested response

- Escalation reason

- Historical context

Definition of Done

- Agent receives a structured escalation package

## Sprint 6 — Security & UAT

Objective: Validate MVP readiness.

Tasks

- PII tests

- Prompt-injection tests

- Security review

- Support SME UAT

- Defect remediation

Definition of Done

- Mandatory safety/security criteria pass

- UAT acceptance criteria met

## Sprint 7 — Pilot

Objective: Measure business impact.

Tasks

- Control/treatment setup

- Controlled traffic

- KPI measurement

- Failure analysis

- Executive review

Definition of Done

- Pilot evidence collected

- Scale/iterate/stop recommendation prepared

# 38. RACI

| Activity | PM | Engineering | ML/AI | Data | Security | Support SME |
| --- | --- | --- | --- | --- | --- | --- |
| Business objective | A/R | C | C | C | C | C |
| PRD | A/R | C | C | C | C | C |
| Model selection | A | C | R | C | C | C |
| Benchmark | A | C | R | R | C | C |
| Routing policy | A/R | C | C | C | C | C |
| Router implementation | C | A/R | R | C | C | — |
| Safety requirements | A | C | R | C | R | C |
| Agent workflow | A | R | C | C | C | R |
| UAT | A | R | R | C | C | R |
| Pilot | A/R | R | R | R | C | C |
| Executive recommendation | A/R | C | C | C | C | C |

A = Accountable, R = Responsible, C = Consulted

# 39. Stakeholder Management

| Stakeholder | Power | Interest | Expectations | Decision rights | Communication |
| --- | --- | --- | --- | --- | --- |
| Executive sponsor | High | High | Business value and risk | Investment | Biweekly |
| Product | High | High | Product outcome | Product policy | Weekly |
| Support leadership | High | High | Resolution/workload | Operational acceptance | Weekly |
| Engineering | High | High | Clear scope | Technical implementation | 2–3× weekly |
| ML/AI | Medium | High | Evaluation clarity | Model evaluation | Weekly |
| Security | High | Medium | Safe architecture | Security approval | At gates |
| Finance | Medium | Medium | Cost model | Economic validation | At business case/pilot |
| Support agents | Medium | High | Useful escalations | UAT feedback | During UAT/pilot |

# 40. Dependency Register

| Dependency | Type | Impact | Mitigation |
| --- | --- | --- | --- |
| Model APIs | Vendor | High | Multi-provider fallback |
| Historical tickets | Data | High | Confirm access early |
| Ticketing integration | Technology | Medium | Prototype early |
| Security approval | Security | High | Start during architecture |
| Support SME availability | Business | Medium | Reserve UAT capacity |
| Benchmark dataset | Data | Medium | Define in discovery |
| Engineering capacity | Internal | High | Capacity check before commitment |
| Provider pricing | Vendor | Medium | Maintain scenario-based economics |

# 41. Risk Register

| Risk | Probability | Impact | Severity | Mitigation | Owner | Trigger |
| --- | --- | --- | --- | --- | --- | --- |
| Complex request routed to cheap model | High | High | Critical | Category thresholds + validation + premium fallback | PM + ML | Quality failure |
| Quality below baseline | Medium | High | High | Benchmark gate + pilot guardrail | PM + ML | Score below threshold |
| Vendor/API outage | Medium | High | High | Multi-provider fallback | Engineering | API failure |
| Savings lower than expected | Medium | High | High | Pilot before scale | PM | KPI misses target |
| Hallucination | Medium | High | High | Validation + authorised context | ML | Incorrect response |
| PII exposure | Medium | High | High | Redaction + security controls | Security | Security test failure |
| Prompt injection | Medium | High | High | Adversarial testing + guardrails | Security + ML | Successful attack |
| Model drift | Medium | High | High | Periodic re-evaluation | ML | Performance deterioration |
| Excessive fallback | Medium | Medium | Medium | Routing calibration | PM + ML | Fallback spike |
| Latency increase | Medium | Medium | Medium | Routing latency budget | Engineering | SLA breach |
| Scope creep | High | Medium | High | Explicit MVP boundaries | PM/PMO | New feature requests |

# 42. Governance

## Model / routing policy change

## Re-evaluation triggers

- Provider pricing changes

- New model release

- Quality deterioration

- Increased fallback

- Changed request distribution

- Safety incident

- Provider outage

- Significant change in context/retrieval behaviour

# 43. Pilot Design

## Control

100% of control traffic uses the premium baseline.

## Treatment

Treatment traffic uses the intelligent routing strategy.

### Compare

- Quality

- AI cost

- Cost/resolved interaction

- Automated resolution

- Escalation

- Fallback

- Latency

- Safety

### Pilot decision matrix

| Outcome | Decision |
| --- | --- |
| Cost improves + quality passes + safety passes | Proceed toward controlled rollout |
| Cost improves + quality close to threshold | Iterate routing |
| Cost improves + quality below threshold | Reject configuration |
| Quality passes + savings too small | Reconsider business case |
| Safety threshold fails | Stop / remediate |

# 44. Launch Plan

## Alpha

Objective: Technical validation.

Users: Internal engineering/AI teams.

Exit: Routing, validation and safety paths work.

## Beta

Objective: Workflow validation.

Users: Selected support agents.

Exit: UAT passes.

## Pilot

Objective: Business validation.

Users: Controlled customer traffic.

Exit: Economic, quality and safety gates pass.

## Production

Objective: Controlled production deployment.

Exit: Stable operating metrics and incident controls.

## Scale

Objective: Expand model coverage and routing categories.

Exit: Continued evidence of economic and customer value.

# 45. Change Management

## Change Request 1 — Add a new RAG system

### Original requirement

Use existing authorised support-context capabilities; no new RAG infrastructure in MVP.

### Requested change

Add a vector database and new retrieval pipeline.

### Impact

- Engineering scope

- Security review

- Evaluation work

- Additional latency

- New operational dependency

### Recommendation

Reject for MVP.

Evaluate dedicated RAG in Phase 2 after validating whether retrieval is a material source of failure.

## Change Request 2 — Automate payment disputes

### Original requirement

High-risk financial issues require human control.

### Requested change

Allow AI to resolve low-value payment disputes autonomously.

### Impact

- Financial risk

- Customer trust

- Compliance/security considerations

- New validation requirements

### Recommendation

Reject for MVP.

Human review remains the control point.

## Change Request 3 — Add another model provider

### Original requirement

Evaluate a defined candidate model set.

### Requested change

Add another provider to the benchmark.

### Impact

- Additional benchmark effort

- Security/vendor review

- Integration work

### Recommendation

Conditional acceptance only if the model has a credible capability/cost advantage and can be evaluated without threatening the pilot timeline.

# 46. Post-Launch Measurement

## AI performance monitoring

- Model quality

- Hallucination

- PII leakage

- Prompt injection

- Safety incidents

- Category-level failures

- Model drift

## Product analytics

- Automated resolution

- Escalation

- Fallback

- Agent workload

- Customer support outcomes

## Business metrics

- AI spend

- Cost/interaction

- Cost/resolved interaction

- Productivity

## Incident management

Critical incidents should trigger:

- Automated protection/fallback where available

- Incident classification

- Technical investigation

- Product impact assessment

- Corrective action

- Model/policy re-evaluation

# 47. Expected Outcome

There is intentionally no fabricated numerical result.

The expected outcome of the MVP is decision-quality evidence answering:

- Can lower-cost models handle meaningful categories of CallE support traffic?

- Can routing reduce premium-model utilisation?

- Can this happen without falling below the quality baseline?

- Do safety guardrails work?

- Does the resulting economics justify the added orchestration complexity?

The project succeeds if it produces enough evidence to make a confident scale / iterate / stop decision.

# 48. Executive Decision Memo

## Recommendation

Approve a controlled 12–16 week MVP/pilot to test intelligent model routing rather than approving a full production rollout upfront.

### Why this solution?

CallE's issue is not simply expensive LLMs.

It is the mismatch between:

Request requirements ↔ model capability ↔ model cost.

A hybrid router addresses that mismatch while preserving human control over risky cases.

### Why now?

The scenario assumes 100,000 monthly AI interactions, making AI unit economics strategically relevant.

### Why AI?

Support requests are expressed in natural language and vary in intent, complexity and context requirements.

### Why this architecture?

It combines:

- Deterministic safety

- AI classification

- Policy-based routing

- Multiple model options

- Validation

- Premium fallback

- Human oversight

### Why this MVP?

It tests the central hypothesis without building unnecessary infrastructure.

### What are we NOT doing?

- New RAG infrastructure

- Autonomous financial actions

- Fine-tuning

- Voice

- Global expansion

- Executive dashboard

### Biggest risk

Routing a complex or high-risk request to an insufficiently capable model.

### Biggest assumption

CallE's interaction population contains enough lower-complexity, lower-risk requests for routing to create meaningful economic improvement.

### What should leadership approve?

A controlled experiment—not a guaranteed cost-saving programme.

# 49. Retrospective & Critical Thinking

## Biggest uncertainty

The actual distribution of CallE requests by:

- Complexity

- Token volume

- Risk

- Context requirement

- Resolution outcome

Without this distribution, projected savings remain uncertain.

## Biggest product risk

A routing policy could optimise average cost while creating unacceptable failures in important support categories.

## Biggest technical trade-off

More sophisticated routing can improve optimisation but introduces:

- More latency

- More orchestration

- More failure modes

- More governance overhead

The router must therefore earn its complexity through measurable economic value.

## Most important assumption

There are enough interactions that can be safely resolved by lower-cost eligible models to justify the added routing complexity.

## What I would validate first with real users

I would validate:

- Whether customers perceive quality differences across model paths.

- Which support categories agents consider unsafe to automate.

- Whether AI-generated escalation summaries actually save agent time.

- Which failure types cause the most rework.

- Whether customers prefer immediate escalation over low-confidence automated answers.

## Data required before further investment

- Actual interaction distribution

- Actual token consumption

- Current premium-model spend

- Baseline quality

- Automated resolution rate

- Escalation rate

- Agent handling time

- Existing retrieval/context architecture

- Security constraints

- Negotiated model pricing

# 50. What I Would Do Differently

If this moved from portfolio simulation to a real product, I would not begin by building the router.

I would first obtain a representative sample of real support interactions and establish:

What percentage of requests actually require premium capability?

Then I would segment those requests by complexity, risk, token volume and resolution outcome.

That data would determine whether routing is worth pursuing.

I would also run the initial experiment offline before changing customer-facing behaviour.

The sequence would be:

Real interaction sample
        ↓
Baseline evaluation
        ↓
Offline routing simulation
        ↓
Failure analysis
        ↓
Controlled pilot
        ↓
Production decision

This reduces the risk of discovering after implementation that the available optimisation opportunity is too small.

# 51. Key Product Decisions

| Decision | Rationale |
| --- | --- |
| Optimise cost/resolved interaction | Avoid false savings |
| Premium model remains baseline | Preserve quality reference |
| Hybrid routing | Combine AI flexibility with deterministic control |
| Risk as a hard gate | Protect high-risk workflows |
| Category-specific evaluation | Prevent averages from hiding failures |
| Premium fallback | Recover safe failures |
| Human escalation | Preserve human control |
| Existing context capability | Avoid unnecessary RAG build |
| No new RAG in MVP | Protect timeline |
| No dashboard in MVP | Prioritise product validation |
| Pilot before production | Evidence before scale |
| Multi-vendor evaluation | Reduce provider dependency |

# 52. Portfolio Artifacts

This case study can be presented with the following supporting visuals:

- Executive problem statement

- Current-state journey

- Future-state journey

- AI opportunity map

- Model evaluation matrix

- Routing decision tree

- Architecture diagram

- PRD / MVP scope

- Prioritisation matrix

- 14–16 week delivery plan

- WBS

- RACI

- Stakeholder map

- RAID / risk register

- Pilot experiment design

- KPI scorecard

- Governance flow

- Executive decision memo

# 53. Final Thesis

The strongest way to describe this project is:

I did not approach the problem as “build an AI router.” I approached it as an enterprise product economics problem: determine whether CallE can use different levels of AI capability for different support requests while maintaining the quality and safety customers expect.

I defined the product strategy, decision criteria, quality thresholds, routing policy, guardrails, MVP scope and experiment design; worked across engineering, ML/AI, security and support stakeholders; and structured a 12–16 week pilot to determine whether the economics justified scaling.

The core lesson is:

Optimisation is not minimising AI cost. It is maximising business value under quality, risk, operational and cost constraints.

### Remaining evidence gap

The case intentionally does not claim:

- Real CallE customer research

- Real CallE production metrics

- Real CallE model spend

- Real CallE benchmark results

- Real CallE savings

- Real CallE ROI

Those would require real organisational data.

That limitation is a feature of the portfolio: it demonstrates that the PM can identify what is known, what is assumed, and what must be validated rather than manufacturing evidence.